## Sheet1
Month | Week | Task | Deliverable | Status
May | 5th Week | Orientation and familiarization with the University of Oulu's 6GVisible project and defining the specific aim, objectives and deliverables for the two month summer training as part of 6GVisible. | - | -
June | 1st Week | Review of Existing Datasets on Network Traffic from Non, Semi, and Fully Autonomous Vehicles. | Datasets for Network Traffic/Usage Prediction | Pending
| 2nd Week | Review of existing ML methods for predicting network traffic from autonomous driving using historical data. | Exisiting ML methods for Network Traffic/Usage Prediction | Pending
| 3rd Week | Develop a network demand predictiion model for 5/6G-enabled autonomous driving. | Customized ML model for Network Demand Prediction | Pending
| 4th Week | Validate and refine the predictive model using available data. | Validated ML model
July |  | Review of 3GPP, ITU standards and parameters for Cellular V2X enabled autonomous driving | Table summarizing the Standards of V2V, V2I, V2N, V2P | Pending
| 2nd Week | Review of existing simulation softwares for assessing 5/6G network capability for massive autonomous driving. | Table summarizing the comparision between 5/6G simulation software tools | Pending
| 3rd Week | Comparision of network simulations of 5/6G enabled autonomous driving with network demand predictions. | Comparision between Network Demand Simulation and Predicition | Pending
| 4th Week | Summarize the findings in a research paper | Research Paper (Draft) and Presentation | Pending